## Sheet1
Cumberland Local Plan 2027-2045 Gateway 1 Readiness Checker
LPA name: | Cumberland Council
Version number: | 1.2
Date: | 2026-10-19
Lead officer | Chris Hoban
Area | Activity | We have made the recommended progress |  | We have started but have a bit more work to do to make the recommended progress |  | We may not have started or have significant work to do to make the recommended progress |  | Notes
Legal requirements you must have met before proceeding | Preparing and publishing a timetable in line with the data standard, publishing a notice of intention to commence and undertaking the scoping consultation | TRUE | We have complied with these legal requirements. | FALSE |  | FALSE | We have not met some or all of these legal requirements. | We have prepared and published a timetable in line with the data standard, published a notice of intention to commence and undertaken the scoping consultation.
Preparing and publishing a local plan timetable | Considering the expected time it will take to adopt the plan | FALSE | The timetable shows how we will prepare and adopt a plan within 30 months. | TRUE | The timetable shows how we will prepare and adopt a plan within 30 months but there are significant risks to this. | FALSE | The timetable shows that preparing and adopting a plan will take substantially longer than 30 months. | The Timetable was published on 30th June and based on the early dates to be a front runner authority (publishing Gateway 1 Self Assessment in October 2026), even though the requirement for Cumberland is the backstop date of April 2026. This came with a number of risks, some of which were significant risks, and some of this remain. These risks include: awaiting guidance from government (especially around what proportionate evidence looks like); delays to the St Cuthbert's Garden Village Local Plan Examination which is impacting on team resources; the time it takes to procure evidence and the availability of consultants to meet very short timescales (shorter than previous); delays to regulations for Spatial Development Strategies meaning the local plan will need to cover more in the earlier stages; and the fact that this is the first local Plan for Cumberland, which also brings in minerals and waste matters, so everything is new - a new local plan for a new area.
Establishing project management and governance arrangements | Establishing appropriate project management, governance and resourcing to support the timetable | FALSE | We have a robust approach to manage, govern, resource and finance the preparation of the plan that supports the delivery of the local plan timetable. | TRUE | We have considered our approach to manage, govern, resource and finance the preparation of the plan, but there are some gaps or an approach is not yet signed off. | FALSE | We have key unresolved questions for how we willl manage, govern, resource or finance the preparation of the plan. | Cross party Member Advisory Group to consider content for the Local Plan; Local Plan Board for project management; delegated authority approved to senior officer (following consultation with Protfolio Holder) for 'process' stages of the new plan making system; seeking to streamline Council approval process for plan content consultation stages; one-off funding to support temporary posts (including a project management role) has been approved. Details of this are included in the PID.
| Testing and agreeing project management and governance internally | FALSE | All relevant teams and decision makers have been involved in designing, and signing-off the approach. | TRUE | Relevant teams and decisions makers have been involved in designing and testing our approach, but it is not yet signed off. | FALSE | We still need to involve other relevant teams and decision makers. | This is largely signed off, and the Local Plan Board meets monthly to review progress and the Timetable, but some changes to the Constitution are still required to streamline the process for Full Council sign off of plan content and final plan stages.
| Establishing risk monitoring, management and mitigation | TRUE | We have identified potential risks and have effective processes in place to monitor, manage and mitigate them. | FALSE | We have identified potential risks and are working to establish processes to monitor, manage and mitigate them. | FALSE | We're still identifying risks or are yet to consider how we will monitor, manage and mitigate them. | More risks will emerge and a number of the existing (and potentially future) risks are outside our control, such as consultant availability and when further guidance etc. is published.
Consulting and engaging on the plan | Preparing an engagement strategy | TRUE | We have a positive strategy for engaging the community and other key stakeholders in the preparation of the plan, which has been prepared with regard to government guidance. | FALSE | We have made some progress in preparing an engagement strategy. | FALSE | We need to start preparing an engagement strategy. | Currently consulting on the draft Engagement Strategy as part of the Scoping Consultation.
| Establishing processes for consultation and engagement | TRUE | We have clear processes in place to maximise diversity in participation, utilising both digital-first and traditional methods. | FALSE | We have scoped out digital-first and traditional methods for engaging with different audiences, but our processes are not yet fully formed. | FALSE | We haven't explored what engagement methods we could use. | We have procured new plan making software which is being installed in the coming weeks. This will expand opportunities for the digital first approach, while also hopefully producing good physical materials, including draft plans, to support plan making and specific consultations. We are also exploring options for community power/greater community involvement in plan making alongside the more traditional methods.
| Agreeing the engagement strategy internally | FALSE | We have sought feedback on and agreed the engagement strategy with key decision makers. | TRUE | We have sought feedback on the engagement strategy with key decision makers, but it's not yet signed off. | FALSE | We still need to seek feedback on our engagement approach with key decision makers. | Engagement Strategy will be updated and finalised in the light of comments received to the Scoping Consultation.
Scoping the anticipated content of the plan | Defining the scope of the plan | FALSE | We understand the proposed scope of the local plan. We know the main areas or locally specific subject matters it will address. This is based on data from the existing local plan, as well as information gathering, baselining and early engagement to date. Scoping work aligns with the work we have carried out on our SEA (if SEA is required). | TRUE | Scoping work is underway. We have reviewed monitoring information for the previous local plan, but still have work to do on information gathering, baselining and early engagement. The scoping work aligns or partially aligns with the work we have carried out on our SEA (if SEA is required). | FALSE | We're only in the early stages of scoping and haven’t considered how this relates to the SEA. | This first Cumberland Local Plan will be a new local plan for a newly defined area, and is not an update to an existing strategy and/or local plan, which means more effort will need to made in understanding the place and options for a strategy. Scoping work for the local plan began in Autumn 2025 with a 10 week public consultation process.
| Drafting a vision for the plan | TRUE | We have used early baselining and engagement activities to begin drafting a vision. | FALSE | Using our baselining work and analysis of feedback from the scoping consultation we have started to develop some ideas about what the vision might focus on. | FALSE | We need to start drafting a vision. | Initial proposals regarding a Vision and Objectives for the Local Plan were included in the Issues and Options consultation that took place during Autumn 2025. This, together with feedback to that consultation and any additional evidence and baseline work will be used to inform a draft Vision for the Plan Content and Evidence consultation stage.
| Considering how we will monitor progress towards the vision | FALSE | We have started to identify measurable outcomes to monitor our progress towards the vision. | TRUE | We have considered how we might monitor progress towards our vision, but haven’t identified specific measurable outcomes yet. | FALSE | We haven’t considered how we will monitor progress towards our vision. | We have begun work to consider outcomes and how they will be measured, and have tried to identify some indicators, primarily through the Integrated Assessment Scoping Report. This will evolve as the plan progresses.
| Gathering evidence to inform the new plan | FALSE | We have mostly identified and scoped our evidence needs and have a plan for how we will deliver this. | TRUE | We have identified some of our evidence needs but still have work to do to scope the work and identify how we will deliver this. | FALSE | We need to start identifying our evidence needs and how we will deliver this. | As Cumberland is still a relatively new place from a statistical it has been difficult finding complete datasets, but work has been done with the information available. In addition to this some local plan evidence base studies has been completed (e.g. General Housing Needs Survey, Stock Condition Survey, Landscape Character Assessment, Waste Needs Assessment), some are being commissioned (e.g. transport baseline) and some are to be commissioned soon (e.g. economic needs assessment, Level 1 SFRA). As we review the national DM policies, our local planning policy framework and local issues we may identify further evidence that may be required to help justify local policies. Details of this are included in the PID.
| Calculating a housing requirement | TRUE | We have calculated a housing requirement for the plan area using the Government's recommended standard method and started to identify the needs for homes of different sizes, types and tenures, including affordable homes. | FALSE | We have calculated a housing requirement for the plan area using the Government's standard method. We haven't started to identify the need for homes of different sizes, types and tenures and affordable homes yet. | FALSE | We haven’t calculated a housing requirement using the Government’s standard method. | The housing need for Cumberland has been calculated using the Government's standard method. The only complicating factor for Cumberland is that it contains half of the Lake District National Park, which is its own planning authority and sets its own housing target. Further work and discussions will be needed with the Lake District National Park LPA to determine how best to disaggregate the Park's needs and provision from the overall Cumberland Council figure.
| Exploring our high-level options and policies | FALSE | We have started to consider high-level and conceptual spatial options to deliver the identified development need, and begun to identify the potential scope of locally specific policies. | TRUE | We have identified the high-level capacity and constraints for development but have not started to develop spatial options to deliver the development need or scoped out locally specific policies | FALSE | We haven’t done any work on high-level spatial options or locally specific policies. | Work on high level options has begun, but needs further work as it is producing a new plan (covering three former districts which had different spatial strategies) rather just updating an existing local plan. The higher level strategy is starting to take form, but further work around key future growth points will be developed further through the plan making process.
Progressing the Strategic Environmental Assessment | Identifying other plans/programmes that have a relationship with the local plan | TRUE | We have identified other relevant plans and programmes and their relationship to the local plan to establish how the plan or programme is affected by those plans or programmes. | FALSE | We have identified other relevant plans and programmes but have not yet analysed how the local plan is affected by those plans or programmes. | FALSE | We have not yet identified other relevant plans or programmes that affect the local plan. | This has been produced in draft as part of the initial work for the draft Integrated Assessment Scoping Report.
| Collecting baseline information for the SEA | FALSE | We have identified baseline information showing the existing environmental characteristics of the area and their likely evolution without implementation of a new plan, as well as data on historic and likely future trends. It provides the basis against which we can assess the likely effects of our different options. | TRUE | We have identified baseline information on the existing environmental characteristics of the area. We have not used this information to establish trends or used it to test the environmental effects of our options. | FALSE | We are in the early stages of (or haven’t yet started) assembling baseline information to inform our strategic environmental assessment. | An initial baseline has been identified, which we would hope to enhance following consultation on the draft Integrated Assessment Scoping Report.
| Identify environmental protection objectives to inform plan preparation | FALSE | We have identified the relevant environmental protection objectives, established at international, community or national level, and environmental considerations that will be taken into account during the preparation of the plan and recorded in the environmental report. | TRUE | We are in the process of identifying relevant environmental protection objectives that will be taken into account when preparing the plan. | FALSE | We have not identified any environmental protection objectives. | A draft set of objectives are incorporated in the draft Integrated Assessment Scoping Report. Consultation is needed to ensure they are effective.
| Developing the scope of the SEA | FALSE | We have begun to identify the scope and level of detail of the information we intend to include in the environmental report. We have started to set out this information in a suitable document, such as a draft, emerging environmental report or scoping document. We are on track to consult on the scope of the SEA at the consultation on proposed plan content and evidence. | TRUE | We’re still working out what the scope and/or level of detail to include in the environmental report. We’re making progress on setting out this information in an appropriate document, but we’re not ready to consult on the scope of the SEA. | FALSE | We have not decided on the scope of the SEA or the level of detail we should include in the environmental report. | The draft Integrated Assessment Scoping Report has been produced and is currently being consulted upon with the statutory consultees.
| Developing SEA objectives | TRUE | We have started to develop SEA objectives which will help assess the environmental performance of the local plan. | FALSE | We have begun to identify the key themes likely to be important when developing SEA objectives to use to assess the environmental performance of the local plan. | FALSE | We have not yet begun on developing SEA objectives to assess the environmenta performance of the plan against. | Draft SEA objectives are included within the draft Integrated Assessment Scoping Report.